## 2018-19 change requests
Priority | Category | Location | Page or Tab | Change Description | Change Request ID
1 | Tweak | Anne & Bill | About Us page | replace the About Us page (Bill and Anne need to supply this text) | T001
1 | Bug | Data | BUG | MASSIVE number of "contact" entries being generated. Go into admin side, and look at 'Contacts'. It is HUGE. What in the heck is causing this??? | B001
1 | Bug | Data | BUG | Latitude Longitude 0,0. Kludgy way he figured out assigning something if Google never returned a lat/long | B002
1 | Bug | Data | Lat/Long | fix all 0/0 lat/long combinations. (bad address & google couldn't find it fast enough). Need a way to find all of those that are currently in the database and fix them | B003
1 | Bug | Parent Side | Detail Page | the map and the location are sometimes out of sink. The map is correct but the camp says it's 5,000 miles away | B004
1 | Bug | Parent Side | Mobile | "Advance Filters" link - doesn't work on the mobile side. Just remove it and have all search features available on mobile | B005
1 | Bug | Parent Side | Results List | a "No camps found" message comes up when camps actually are found. | B006
1 | Bug | Parent Side | Search criteria | Search is still messed up | B007
1 | Tweak | Parent Side | Detail Page | When the date is past, is seems that the date field is then just blanked out. Should we maybe say 'This camp has concluded' or something? Not sure what it should say, but something that indicates that there's a reason the date is blank. | T002
1 | Tweak | Parent Side | Detail Page | The dates are blank; please put them back on the display page. All camps should be shown from 1/1/2018 till now | T003
1 | Tweak | Parent Side | Detail Page | Dates should show full year "2018". (ex. 06/18/2018 - 06/22/2018" | T004
1 | Tweak | Parent Side | General | remove ads from page bottom - all pages. No AdSense ads anywhere! | T005
1 | Tweak | Parent Side | Results List | Results need to have "page 1 of x" part at the bottom. | T006
1 | Tweak | Parent Side | Results List | Results list needs to actually have ALL results available to view. In other words, I think right now it returns the first 100, and never any more than that. Even if there were 500 matches, you can never go to a next page and see anything more. It used to allow you to do that. We would like that functionality restored. I believe it was originally removed due to performance concerns. We want to find a different way to deal with performance that doesn't take that functionality away. | T007
1 | Tweak | Parent Side | Results List | Activate the "Page 1 of X" feature - Currently it is only displaying the first 50 items, and not allowing to go to subsequent pages. | T008
1 | Performance | Technology | Technology | Generally address the slowness of the site | PS001
1 | Stability | Technology | Technology | SERVER: We have a "self-managed" hosted server, but we don't know how to "self-manage" it! | PS002
1.1 | Tweak | Upgraded Camp | Camp Detail Page | Mock up an example that we can show people | T009
1.1 | Stability | Technology | Technology | SERVER: Open to moving it somewhere else. We also have a test domain. | PS003
1.1 | New Feature | Upgraded Camp | Camp Detail Page | Camp Description, label suggestions… suggested sections which will be put into the descirption if they've entered something. For example, Company overview, philosophy, space/building, leader bios, etc. | F001
1.1 | New Feature | Upgraded Camp | Camps Rock Home Page | put some reviews of the upgraded camps at the bottom of the search page. | F002
1.1 | New Feature | Upgraded Camp | Camps Rock Home Page | On search page, a horizontal featured list at the bottom. Can click arrows to scroll side-to-side. "Featured" that match the search criteria, logos clickable, etc. Sort of like "related items" in Amazon (below what you clicked into). Randomize which one is up first. | F003
1.1 | Tweak | Upgraded Camp | Camp Detail Page | make the background nicer with some color. Rigth now it's somewhat bland. The free listings will stay "bland" :) | T010
1.1 | Tweak | Upgraded Camp | Camp Detail Page | a button that takes you to their website. Visible and nice | T011
1.1 | Tweak | Upgraded Camp | Camp Detail Page | Are there any improvements that could be made with the photo carousel? Size of pictures maybe? | T012
1.1 | Tweak | Upgraded Camp | Camp Detail Page | image and logo on header (look at linked in for example). All of it bigger and more impressive looking | T013
1.1 | Tweak | Upgraded Camp | Results List | Logo bigger, better, faster :-) oversize | T014
1.1 | Tweak | Upgraded Camp | Results List | Box around logo to separate it from everything else | T015
1.2 | Tweak - ANNE | DMC Website | Director Mem Club | redo the page that shows the cost - figure out what it's going to say | T016
2 | Tweak | Anne & Bill | terms & conditions | Terms & Conditions - rewrite them. Also verify that it's written in T&C that we can contact them via email (thus can put them into ConvertKit) | T017
2 | Bug | Director Side | Publish | apostrophe problem - allow apostrophes in the camp name field (director side data entry). single quote in camp name - can't publish - actually doesn't even notify you that there was a problem | B008
2 | Data Entry | Director Side | Importing camp data | import large amout of data - like, thousands of camp from one organization (could be hundreds, up to many thousands) | D001
2 | Data Entry | Director Side | Importing camp data | NEED: to be able to import or use their data from last year (or previous year) | D002
2 | Data Entry | Director Side | Importing camp data | NEED: to be able to capture the parent comments from individual camps, and also parents who have 'favorited' camps. | D003
2 | Tweak | Director Side | Date/Time tab | date range - Start with 3 date ranges open on the date/time tab. | T018
2 | Tweak | Director Side | Dates/Times Tab | Camp type radio button - Change the camp type from drop down to radio buttons. Have them select "Full Day" , "Half Day", or "Overnight… radio button so that all three are visible. Default is Full Day. As it currently is, people are blowing by this control and they are leaving it as the default. | T019
2 | Tweak | Director Side | Registration page | check box on Registration. Have users forced to check a confirmation that they agree to terms & conditions | T020
3 | Data Entry | Back End | Admin. Camp Display | when we move camps from one year to the next, keep a copy of the old camp. We want to have counts and such. | D004
3 | New Feature | Back End | Admin mode | drop down for camp org - put on all list of camps (admin account) | F004
3 | New Feature | Back End | Admin mode | Camp List page - have org drop down to show just those camps for that org. | F005
3 | New Feature | Back End | Admin. Camp Display | Filters (unplublished, published w/problems, years (ie show all 2017), Number of camps listed) | F006
3 | New Feature | Back End | Data for Anne & Bill | Report: who is registered, who has camp but didn't publish, who publilshed, etc. | F007
3 | New Feature | Back End | Data for Anne & Bill | How many published? Who Published something today? | F008
3 | New Feature | Back End | Report | Back end capture of some statistics… For example, every click into their detail page. Every click to their website. | F009
3 | New Feature | Back End | Report | Somehow a report (available to us on back end) to see what bad data there is | F010
3 | New Feature | Back End | Superusers | superuser password - Give us a superuser password where we can look at the account as though we are that camp director. Currently we can log in as ourselves (back end), but we are seeing everything. We want it to be more like exactly what THAT director would be seeing. Also that we can change anything about it | F011
3 | Tweak | Back End | Report | admin page for Organizations, need more info - in Organization List (name, email address, org name, date) - to import to ConvertKit | T021
3 | Tweak | Back End | What is this? | We want this to stay off for now; Is the register email back verifing or is it still off - this note is old, and I don't remember what it means, but may be important to check this out! | T022
4 | New Feature | Parent Side | Detail Page - FHO | display Camp Type in preview - On the Preview page, we need to display half day, full day, or overnight text. Put the text between "Days:" and "Times:" | F012
4 | New Feature | Parent Side | Search criteria - FHO | Be able to search on full day, or half day, or overnight, and maybe filter by those. How do we define full day versus half day? | F013
4 | New Feature | Parent Side | Search criteria - FHO | search type of camp - Full day, half day, buttons at the bottom of the search criteria | F014
4 | New Feature | Parent Side | Search criteria - FHO | Full, Half, and Overnight controls - This refers to how Vijay originally coded this. All of the description/functionality below has currently been turned off/hidden from view. Change the indicators to say 'On' and 'Off' Change the colors to be yellow in either direction (no brown/orange, just all yellow regardless of On or Off) Change 'Off' text to be black, just like the 'On' side. Change default to all say 'On' When someone comes into search from scratch, the functionality always starts by searching and returning everything in the database. Only filter when they turn someting Off. | F015
5 | Tweak | Parent Side | Search criteria - AGE | We need to revisit the whole grade/age issue? I think people didn't really understand how to use it. | T022
5 | Tweak | Parent Side | Search criteria - AGE | AGE and GRADE tied together - A parent cannot search only on age, or only on grade. These two fields are tied together. If they want to search for age, they also are required to enter grade. If they want to search by grade, they are required to enter age. We would like both of those scenarios to turn the offending field RED, and put a message underneath that says "Age and Grade are both required together" | T023
5 | Tweak | Parent Side | Search criteria - AGE | Age and Grade - Remove the option 'None' | T024
5 | Tweak | Parent Side | Search criteria - AGE | Age and Grade - Have the default word on that control be -Select- | T025
5 | Tweak | Parent Side | Search criteria - AGE | Age and Grade boolean logic - The boolean logic for age (alone) is AND … in other words, if they check 7 yr old, and also 9 yr old, the search would return camps that apply to BOTH 7 and 9 year olds. The same is true within Grade… if they select more than one grade, it is an AND. 2nd grade and 4th grade both included in the same camp. Between Age and Grade, the boolean logic is OR. So, if they choose 7 yr old on age, and 2nd grade on Grade, the search would return all camps for 7 year olds, OR camps for 2nd graders (all inclusive, every possible camp for those two conditions). The logic for multiple ages (AND), and the logic for multiple grades (AND) is applied separate from the logic for the two combined (OR). [NOTE: some camps only go by grade, and some only by age, and some specify both age and grade... those are all inclusive] | T026
5 | Tweak | Parent Side | Search criteria - AGE | AGE and GRADE tied together - A parent cannot search only on age, or only on grade. These two fields are tied together. If they want to search for age, they also are required to enter grade. If they want to search by grade, they are required to enter age. We would like both of those scenarios to turn the offending field RED, and put a message underneath that says "Age and Grade are both required together" | T027
6 | Bug | Director Side | Edit Location | Editing location, the State didn't change back - I changed an address to one that is in Pennsylvania. When I changed it back to one here in Centerville, it did take the city and zip, but it didn't change the state back from PA to OH. | B009
6 | Bug | Director Side | Location tab and/or Registration | sponging an address; the state is not getting saved.- double check this - could be fixed | B010
6 | Bug | Director Side | Preview | Map Not showing correct address - When a camp is cloned and a new address is put in, if Google doesn’t recognise the new address it will display the entered address (text) but show the last address in the map. | B011
6 | Bug | Director Side | Registration | State not being saved on the Organization | B012
7 | Bug | Director Side | Add Camp | Add Camp [+] button disappears - Need further testing to positively recreate this. | B013
7 | Bug | Director Side | Amenities Tab | Special Needs, &amp - When selecting the Special Needs of ADHD & Similar, after selecting it, it says 'ADHD &amp …' | B014
7 | Bug | Director Side | Dates/Times Tab | Start Date Calendar feature - On Add Camp, the Start Date calendar feature doesn't come up. End Date works fine. We have recreated this problem in both Firefox and Edge. Once the camp is added, and you go back in through the Edit link, the calendar pops up fine. Maybe put 01/01/2018 in the field. (not a show stopper but it's embarrassing) | B015
7 | Bug | Director Side | Dates/Times Tab | An invalid date in the date range gives an error. I put start date 07/01/123. End date 01/01/1 The error was in a popup box. Not sure which one caused that. | B016
7 | Bug | Director Side | Ribbon Mode | Change Next button to Save - Rather than Next, label the button in the ribbon mode to 'Save', and have it not go back to tab mode. Right now if you click Next, it changes the display back to tab mode. So, if you ever use the Next button, you don't stay in ribbon mode. | B017
7 | Bug | Director Side | Saving/edit - camps | changing tabs, hitting "+", or back to list button, etc - must save the camp. This was fixed and now is not. | B018
7 | Data Entry | Director Side | Amenities Tab | Limit text length for 'Special Needs' on the detail page - training issue for data analysts | D005
7 | Tweak | Director Side | Criteria tab | min max grade, min max age … find notes (an option past 12th grade, age past 20 years old) | T028
7 | Tweak | Director Side | Description Tab and Dates Tab | Date fields: auto location of end date - On Dates, After entering a start date, calendar automatically adjusts to no earlier than the start (on both the camp dates, and the registration dates) | T029
7 | Tweak | Director Side | Price Tab | Discount description on pricing tab needs to be limited to 100 characters | T030
7 | Bug | Parent Side | General | Parent login give an object error | B019
7 | New Feature | Parent Side | General | Use another service to login' … facebook, google, etc. Can those be more standard? I haven't tried them… do they work? Or, worst case, just remove those altogether. | F016
7 | New Feature | Parent Side | Results List | Could we add sort by price? What other sorting? | F017
7 | New Feature | Parent Side | Results List | Parent ratings (stars) on the results list? And maybe be able to sort by them? | F018
7 | New Feature | Parent Side | Results List | Place Star Rating as an item on the "card", which is to the right of the Theme item, and above the Cost (Show Price) item. If possible, have this display the five stars with the yellow indicating the average stars | F019
7 | New Feature | Parent Side | Search criteria | Clear All button - If it is possible. If this is challenging, don't worry about it. But, if there is a way to add a Clear All Button, I would want to put it right under the three controls for Full Day, Half Day, and Overnight. Same size and shape as 'Find Camps', but underneath 'Overnight' control. | F020
7 | Tweak | Parent Side | Detail Page | Instead of "Unavailable" for Discounts, Extended Care, Lunch, and Special Needs, could those just not show up at all if they don't apply or aren't available? | T031
7 | Tweak | Parent Side | Detail Page | Slightly re-organize the 'Camp Information' box on the detail page - we can talk about this | T032
7 | Tweak | Parent Side | Detail Page | there is a dash following some days of the week (ie "Sat -"). Also make sure all combinations of days are covered. | T033
7 | Tweak | Parent Side | Detail Page | showing price - "Full Price - $200" vs "200 - Full Price" | T034
7 | Tweak | Parent Side | Detail Page | Pricing list all price options For pricing, if they have listed up to three different choices, list all the options they gave us, label: $xx.xx So, it would say: Pricing: Full Price: $125 Resident Price: $110 Military Price: $90 | T035
7 | Tweak | Parent Side | Detail Page | Change the Registration section Similar to Pricing above, Change the Registration information to look like this: Registration: Opens: 01/01/2018 Closes: 05/05/2018 It's ok if the dates don't line up. Not an issue. If the Closes date is blank, just leave it blank. | T036
7 | Tweak | Parent Side | General | Would love to have the fonts larger in the data entry spaces. Actually fonts larger everywhere would be great. | T037
7 | Tweak | Parent Side | Parent Reviews | Parent reviews, white box too small - On the Parent Reviews, the white box is too small for a long review. Check Dayton International Peace Camp for example. Just needs to be another few clicks bigger. | T038
7 | Tweak | Parent Side | Results List | Deal with discounts on results list? Need to discuss | T039
7 | Tweak | Parent Side | Results List | Change the label that currently says 'Cost' to be whatever label the camp org had selected on the price tab as their desired "Show Price". Use that label and that price on the results list (the "card") | T040
7 | Tweak | Parent Side | Search criteria | Double check what is listed in results "theme" line… it should be the main theme as defined by the camp director | T041
7 | Tweak | Parent Side | Search criteria | search by Date fields: auto location of end date - On Dates, After entering a start date, calendar automatically adjusts to no earlier than the start | T042
7 | Tweak | Parent Side | Search criteria | Keyword search allow more words - The old keyword search was not very smart… it would only look for *exactly* what you entered. So, if you entered 'fun camp', it literally only looked for those two words together with a single space between. We would like this to be just a little more smart, and be able to take each individual word and put an 'AND' in between. So, searching for 'fun camp', would actually search for anything that says 'fun' and 'camp', both, anywhere in the text. | T043
7 | Tweak | Parent Side | Search criteria | Keyword search needs to search in Camp Name, Org Name, and Special Needs Description - The keyword search function needs to look at all text in the Organization Name, and the Camp Name, and the camp description, and the special needs description… all four. | T044
7 | Bug | Upgraded Camp | Camp Detail Page | Photo carousel has trouble when only one photo has been loaded | B020
7 | Bug | Upgraded Camp | Logo/Photo tab, Director Side | I attached a logo file that was an excel spreadsheet… created an error. Once I had that error, I couldn’t get rid of it. | B021
7 | Data Entry | Upgraded Camp | Camp Data Entry | Need to come up with specs on sizes of images for upgraded pages… logo, favicon, and photo carousel | D006
8 | New Feature | Parent Side | Favorites List | More summary info on the My Favorites page… like, as much as there is on the results list | F021
8 | Tweak | Parent Side | Favorites List | Feedback that something was added to the favorites list if you were not logged in at the time of clicking 'Add to Favorites'. It does add it, it just doesn't indicate to you that it worked. | T045
8 | Tweak | Parent Side | Favorites List | More obvious way to get back from viewing My Favorites to the page you were just looking at? (back arrow works, but we should provide something more clean) | T046
8 | Tweak | Parent Side | Favorites List | Several things I'd like to change about how the 'My Favorites' works. | T047
8 | Tweak | Parent Side | Favorites List | When you click 'Add to Favorites' and you're not logged in, could it go to something other than the regular login page. Maybe something like, 'Please log in or create an ID to save your favorites' | T048
8 | Tweak | Parent Side | Search criteria | Special Needs selection control - Display a selection control (exactly like the theme control), for the special needs options. The default would say -Select- These would be the same type of checkboxes in a drop down menu. This functionality should be 'OR' (return as many as possible that match any of the Special Needs items that they identify) Place this control After Date range and above the camp types | Done?
8 | Tweak | Parent Side | Search criteria | Theme Search, Remove -Select Theme- option as the first checkbox. | T049
8 | Tweak | Parent Side | Search criteria | Theme Search should be OR - All theme searches (if they choose more than one), should be OR'd together (not AND). | T050
8 | Tweak | Parent Side | Search criteria | Subtheme Control problems - You can only open or close one topic, and then the collapse feature doesn't work again. | T051
8 | Tweak | Parent Side | Search criteria | Expanded Subthemes match themes - When someone clicks into Subtheme, the only Subthemes that are expanded are the ones for the Themes that they selected in the above theme selection. The other themes can be there, but not expanded. | T052
8 | Tweak | Parent Side | Search criteria | They can select any subtheme - If it works this way, that's fine, this is not required. But, if they didn't select the theme, but then they're in the subtheme field and end up expanding something different and selecting something in another theme, that is fine. Just add that subtheme to the search. Again, only if that's easy or the way it already works. | T053
8 | Tweak | Parent Side | Search criteria | Theme and Subtheme independent fields - Theme and subtheme work separately (in terms of how parents can use them to select)… they can do one, or the other, or both. If they start by using theme, then choose subthemes, and then later go up and remove the theme, those subthemes would still be selected. | T054
8 | Tweak | Parent Side | Search criteria | Special Needs selection control - Display a selection control (exactly like the theme control), for the special needs options. The default would say -Select- These would be the same type of checkboxes in a drop down menu. This functionality should be 'OR' (return as many as possible that match any of the Special Needs items that they identify) Place this control After Date range and above the camp types | T055
x? | Bug | Director Side | Entering Camps | Next button -IE has problems with "Next" button - creating multiple camps and confusing the user (and us). | Fixed?
x? | Bug | Director Side | Theme tab | identical theme's, different subtheme's not working - you can have one instance of a theme saved, even if you want multiple sub-themes in that theme. For example try saving traditional, multitopic and motivational in two themes. It would only save one. Themes need to be sticky on the Camp editing page. | Fixed?
x? | New Feature | Director Side | Camp Entry | Would like to enter the Camp Org information first, and then individual camps after. | Done?
x? | New Feature | Director Side | Camp Entry | Some method where they can do it a little bit at a time, and we can automatically remind them to come back and finish. Perhaps use a "grid", very much like a spreadsheet, but they are mostly very uncomfortable with spreadsheets! Most camps just have one, two, or three offerings, but then we also have some that have as many as 50 or more different camps! The average # of camps per organization is 9 | Done?
x? | New Feature | Director Side | Date/Time tab | Overnight camps … possibly have different time/date needs - need to brainstorm solutions | Fixed?
x? | New Feature | Director Side | Edit Camp | The camp to be able to maintain their own info throughout the year (like mark their camp as full, or waiting list, or something like that)
x? | Tweak | Director Side | Date/Time tab | AM/PM camp times - Somehow need to find a way to deal with this so we don't have to enter two camps the same, maybe a camp type of '1/2 Day' or something like that | Fixed?
x? | Tweak | Parent Side | General | Make 'Register a new user' be a button rather than clickable text | Done?
x? | Tweak | Parent Side | General | The color of the Register, Login, and Hello Admin! Along the top is too light, hard to see/notice | Done?
x? | Tweak | Parent Side | Results List | Grade on results list and detail pages - Please change grade to the format 5th, rather than Fifth. So, 1st, 2nd, 3rd, 4th, etc. (on the "card") | Fixed?
x? | Tweak | Parent Side | Results List | Results side - right side - Display box (the white area) match up with the length of the left side box (criteria area) | Fixed?
x? | Tweak | Parent Side | Search criteria | Add in any distance from zip (to accommodate overnight camps anywhere in the country). Right now max is 150 | Fixed?
x? | Tweak | Parent Side | Search criteria | Different cities, are the zip code and distance from zip going to work ok going to four new cities? | Done?
x? | Tweak | Parent Side | Search criteria | The way the zip code/address field works. Clunky right now, need to improve. | Done?
x? | Tweak | Parent Side | Search criteria | Label "Zip Code" to "Address or Zip Code" - Change the label on 'Zip Code' to 'Address or Zip Code' Also, change the prompt inside the data entry to "Enter an address, city, or zip" | Done?
x? | Tweak | Parent Side | Search criteria | Change Distance default to 10 miles - currently set to 30 (not sure, has this already been changed?) | Done?
x? | Tweak | Parent Side | Search criteria | Change the 150 mile distance to unlimited | Done?
Z | New Feature | Overall | Org Page | Create a page that shows the organizations and all it's camps.
Z | New Feature | Overall |  | Camps Rock data is currently centered mostly around the CAMPS. Would like to be centered more on the Camp Organization, with the camps attached to it, so that parents can look at everything that is offered by that camp as well as looking at camps individually | F022
Z | New Feature | Parent Side | Detail Page | Email the director button. We actually create the email for them, and don't give out the email addresses at all. | F023
Z | New Feature | Parent Side | Detail Page | We thought of something like, the user can't get the director's email address and phone number unless they sign up for Camps Rock. When they are signed up, then those fields are visible on all. | F024
Z | New Feature | Parent Side | General | A way for someone to share a camp on Facebook (with a link to that camp's detail page) | F025
Z | New Feature | Parent Side | General | Put a Like Us button for facebook, twitter, etc. The ones we have there just go to our page. Wondering if we can actually have it do the 'Like'. That may not be possible, I don't know how these things work. :) | F026
Z | New Feature | Parent Side | Results List | Toggle results list from normal view to first lines of description view | F027
Z | New Feature | Upgraded Camp | Camp Detail Page | possibly list each camp orgs Twitter, FaceBook, etc from the camp view. Like Brilliant Directories does. | F028
Z | New Feature | Upgraded Camp | Camp Detail Page | Images, Maybe display images more like Facebook does, and when you click it takes you to a display of all (more like a folder) | F029
| Category = Data Tweak Bug New Feature/Function Performance | Location = Parent Side Director Side Back End Technology DMC Website Upgraded Camp